## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint -1 | Sprint-1 | US1 | As a system, I want to setup project repository and environment so that development can begin | MUST HAVE | None | AnandKumar | 3- Completed
Sprint -2 | Sprint-2 | US2 | As a system, I want to integrate Whisper STT to convert calls to text | MUST HAVE | US1 | GuruKrishna | 3- Completed
Sprint -3 | Sprint-3 | US3 | As a system, I want to clean and preprocess transcripts for analysis | SHOULD HAVE | US2 | Udayasree | 3- Completed
Sprint -4 | Sprint-4 | US4 | As a system, I want to define structured schema for storing transcripts | SHOULD HAVE | US3 | Varshasree | 3- Completed
Sprint -5 | Sprint-5 | US5 | As a system, I want to implement LLM scoring for empathy and compliance | MUST HAVE | US4 | GuruKrishna | 3- Completed
Sprint -6 | Sprint-6 | US6 | As a system, I want to design prompts for evaluation | MUST HAVE | US5 | AnandKumar | 3- Completed
Sprint -7 | Sprint-7 | US7 | As a system, I want to build RAG pipeline using LangChain | MUST HAVE | US6 | AnandKumar | 3- Completed
Sprint -8 | Sprint-8 | US8 | As a system, I want to integrate knowledge base for contextual audits | SHOULD HAVE | US7 | GuruKrishna | 2- In Progress
Sprint -9 | Sprint-9 | US9 | As a system, I want to develop dashboard UI for analytics | MUST HAVE | US7 | Udayasree | 2- In Progress
Sprint -10 | Sprint-10 | US10 | As a system, I want to visualize agent performance metrics | SHOULD HAVE | US9 | Udayasree | 2- In Progress
Sprint -11 | Sprint-11 | US11 | As a system, I want to implement alert system for compliance issues | MUST HAVE | US10 | Varshasree | 3- Completed
Sprint -12 | Sprint-12 | US12 | As a system, I want to generate PDF/Excel reports | SHOULD HAVE | US11 | Varshasree | 3- Completed
Sprint -13 | Sprint-13 | US13 | As a system, I want to test the entire system for bugs | MUST HAVE | US12 | Varshasree | 2- In Progress
Sprint -14 | Sprint-14 | US14 | As a system, I want to deploy the application | MUST HAVE | US13 | AnandKumar | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
\
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 164 | 11 | 18 | 15 | 15 | 14 | 13 | 20 | 14 | 8 | 7 | 8 | 7 | 12 | 4
SPRINT 1 BACKLOG
US1 | T1 | Setup project repository | 2026-02-10 | 2026-02-11 | AnandKumar | Setup | Done | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1 | T2 | Setup development environment | 2026-02-11 | 2026-02-12 | AnandKumar | Setup | Done | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | T3 | Integrate Whisper STT | 2026-02-12 | 2026-02-14 | Udayasree | Development | Done | 10 | 0 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | T4 | Convert audio to text | 2026-02-14 | 2026-02-15 | Udayasree | Development | Done | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | T5 | Clean transcripts | 2026-02-15 | 2026-02-16 | Varshasree | Processing | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | T6 | Define Schema | 2026-02-16 | 2026-02-17 | GuruKrishna | Design | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
SPRINT 2 BACKLOG
US5 | T7 | Implement LLM scoring for empathy | 2026-02-24 | 2026-02-26 | GuruKrishna | Development | Done | 10 | 2 | 2 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US5 | T8 | Implement compliance scoring | 2026-02-26 | 2026-02-28 | Udayasree | Development | Done | 8 | 0 | 0 | 0 | 3 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US6 | T9 | Design prompts for evaluation | 2026-02-28 | 2026-03-02 | AnandKumar | Design | Done | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 1 | 0 | 0 | 0 | 0 | 0
US6 | T10 | Optimize prompt responses | 2026-03-02 | 2026-03-04 | AnandKumar | Development | Done | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0
US5 | T11 | Test scoring outputs | 2026-03-04 | 2026-03-06 | Varshasree | Testing | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0
US5 | T12 | Debug scoring issues | 2026-03-08 | 2026-03-09 | Varshasree | Testing | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0
SPRINT 3 BACKLOG
US7 | T13 | Build RAG pipeline | 2026-03-10 | 2026-03-13 | AnandKumar | Development | Done | 10 | 4 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US7 | T14 | Integrate LangChain | 2026-03-13 | 2026-03-15 | AnandKumar | Development | Done | 8 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US8 | T15 | Connect knowledge base | 2026-03-15 | 2026-03-17 | Varshasree | Development | Done | 8 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US9 | T16 | Develop dashboard UI | 2026-03-17 | 2026-03-20 | GuruKrishna | Development | In-progess | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 1 | 0 | 0 | 0
US10 | T17 | Create analytics charts | 2026-03-20 | 2026-03-23 | Udayasree | Development | Done | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2
SPRINT 4 BACKLOG
US11 | T18 | Implement alert system | 2026-03-24 | 2026-03-27 | AnandKumar | Development | Pending | 8 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US12 | T19 | Generate PDF reports | 2026-03-27 | 2026-03-30 | Varshasree | Development | Pending | 8 | 0 | 0 | 2 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US13 | T20 | Generate Excel reports | 2026-03-30 | 2026-04-01 | Udayasree | Development | Pending | 6 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US13 | T21 | System testing | 2026-04-01 | 2026-04-04 | GuruKrishna | Testing | Pending | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | 0 | 0 | 0
US14 | T22 | Deployment | 2026-04-04 | 2026-04-06 | AnandKumar | Development | Pending | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Setup issue | Installed tools
Sprint 1 | Day 2 | STT error | Fixed API
Sprint 2 | Day 3 | Data issue | Cleaned data
Sprint 2 | Day 4 | LLM issue | Tuned prompt
Sprint 3 | Day 5 | Wrong output | Improved logic
Sprint 3 | Day 6 | RAG issue | Checked docs
Sprint 4 | Day 7 | DB issue | Fixed index
Sprint 4 | Day 8 | UI bug & Deploy issue | Debugged UI & Fixed setup

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-10 | 2026-02-23 | AnandKumar | Better planning | Delaying setup | Team coordination | Plan early
2 | Sprint 1 | 2026-02-10 | 2026-02-23 | Udayasree | Debug faster | Ignoring errors | API integration | Fix early bugs
3 | Sprint 2 | 2026-02-24 | 2026-03-09 | Varshasree | Improve prompts | Rework tasks | Coding practice | Optimize logic
4 | Sprint 2 | 2026-02-24 | 2026-03-09 | Udayasree | Test outputs | Skipping tests | LLM scoring | Add test cases
5 | Sprint 3 | 2026-03-10 | 2026-03-23 | GuruKrishna | Improve UI | Delay UI fixes | Dashboard work | Debug UI
6 | Sprint 3 | 2026-03-10 | 2026-03-23 | AnandKumar | Learn RAG | Confusion in docs | Integration | Study docs
7 | Sprint 4 | 2026-03-24 | 2026-04-06 | Varshasree | Test early | Late testing | Bug fixing | Increase testing